**Toward Right Relationship with Native Peoples (TRR)**

 **Work Plan and Budget, 2017**

**(Oct. 1, 2016 – Sept. 30, 2017)**

**History and Development of the Toward Right Relationship Project**

*“What really is needed is greater awareness by the broader American public…of the continuity of Indigenous Peoples within the American social political fabric…and reconciliation for the historical and ongoing wrongs that have occurred….The consequences of these wrongs are manifested in the socio-economic disadvantages that Indigenous peoples face….With greater awareness, people can take actions that are appropriate to their local circumstances.”*

 -- James Anaya, the UN Special Rapporteur for Indigenous Peoples Rights

In response to such calls from Indigenous leaders, the Toward Right Relationship Project is working to raise awareness about historical and ongoing injustices committed against Native Peoples and seeking ways to build right relationship with them in accord with the UN Declaration on the Rights of Indigenous Peoples.

Quakers have a long history of seeking right relationship with Native Peoples, but we might ask ourselves the question Lucretia Mott posed to the Abington Peace Meeting in 1869: *“I wonder if, with the profession we Friends have made of care for the Indians, we have been active enough in our labor?”*

Boulder Friends have held a concern for the rights and wellbeing of Indigenous peoples since the mid-1990s when the Native American Concerns Committee formed. Many Boulder Friends have served on this committee, which changed its name to Indigenous Peoples Concerns in recognition of the global issues facing Native peoples everywhere. In 2012 the committee undertook study of the impacts of the Doctrine of Discovery and the United Nations Declaration on the Rights of Indigenous Peoples. They drafted a Minute that would repudiate the Doctrine of Discovery and support implementation of the UN Declaration, with the intention of offering it for consideration by monthly meetings within Inter-Mountain Yearly Meeting. Under a clear and strong leading, IPC committee member Paula Palmer began devoting full time to researching, consulting with Native American educators and other advisors, and working with them to develop an educational workshop that could help meetings understand these issues and prepare to take action on them. She began presenting her workshops in January 2013. Inter-Mountain Yearly Meeting and several monthly meetings, including Boulder Meeting, have since approved minutes repudiating the Doctrine of Discovery and supporting implementation of the UN Declaration on the rights of Indigenous Peoples.

In April 2013, Paula met with a Clearness Committee, and in May the Meeting approved the Clearness Committee’s report, recognizing Paula’s work as a spiritual leading. The Meeting also established a restricted Toward Right Relationship Fund, where people can give tax-deductible donations to support this work. In October 2014, the Boulder Meeting approved a Traveling Minute for Paula Palmer as she travels in ministry with the Toward Right Relationship project. The Meeting also established an Oversight Committee that oversees the TRR fund and Paula’s work as director of the Toward Right Relationship project, and a Spiritual Care Committee that provides spiritual support to Paula as she carries out her ministry. In October 2013, Paula and the Meeting signed a one-year renewable contract for her compensation as director of the Toward Right Relationship project. Since then, the meeting has approved renewal of the contract year by year.

Since 2014, two Native American women (Jerilyn DeCoteau, Ojibwe/Cree, and Doreen Martinez, Mescalero Apache) and an Episcopalian lay volunteer (Ann Cairns) form a TRR Outreach team, promoting and facilitating workshops in Native communities, faith communities, schools and colleges. A TRR Facilitators Network has been formed of volunteers trained and certified by Paula who are now presenting Toward Right Relationship workshops through their religious, civic, and educational networks. Three versions of the workshops (one for adults in the general population; one for middle school and high school students; and one for Native groups) have been presented more than 120 times in 18 states.

In 2015, Paula was awarded Pendle Hill’s Cadbury Scholarship and Swarthmore College’s Moore Fellowship to conduct research on the roles Quakers played during the era of the Indian boarding schools. She proposed this research in response to a call from the National Native American Boarding School Healing Coalition, and she is working in close collaboration with Native people who are seeking truth, reconciliation, and healing. In April 2016, she began reporting on her research through slide presentations and articles for publication.

**Toward Right Relationship Project Mission:**

* To publicize, promote, and present the “Toward Right Relationship with Native Peoples” workshops as educational tools; create opportunities to present the programs throughout the country; and train religious, civic, and educational groups to conduct the workshops for educational purposes.
* To coordinate with Native Americans and other organizations to create and/or support meaningful processes for social change, healing, and right relationship among all the peoples of this land.

**2017 Toward Right Relationship Project Work Plan**

**October 1, 2016 – September 30, 2017 (Fourth Year)**

**Objectives**

1. Discern, through prayer, worship, and consultation with my Spiritual Care Committee and other seasoned Friends, how to faithfully serve in the ministry of building right relationship with Native peoples.
2. Raise funds to support this work plan and meet the budget through individual and group donations, grants, honorariums, and social media fundraising strategies.
3. Present the three TRR workshops -- “*Roots of Injustice, Seeds of Change: Toward Right Relationship with America’s Native Peoples*” (for adults in the general U.S. population), “*Re-Discovering America: Understanding Colonization”(*for middle schools, high schools, and religious education programs), and *“Native History; Native Rights: Roots of Injustice, Seeds of Change,”*(for Native American communities, organizations, and tribal colleges) at least 25 times, hosted by faith communities, educational institutions, and Native organizations around the country. Note: These presentations will be given by Paula and by other TRR workshop facilitators who are trained and certified.
4. Train, certify, and coach at least 10 people to present the Toward Right Relationship workshops on their own as part of the TRR Facilitators’ Network.
5. Build a support and communications system for the TRR Facilitators Network, so that facilitators continue to share and grow in effectiveness together.
6. Report findings of research on the Quaker Indian Boarding Schools through slide presentations, a film of the slide presentation, the TRR webpage, articles, pamphlets and academic papers.
7. Collaborate as needed with the Native American Rights Fund and the National Native American Boarding School Healing Coalition to report the recorded deaths of Native children at Quaker Indian Boarding Schools and their burials, and inform Friends of our obligation to comply with the requirements of the Native American Graves Protection and Repatriation Act.
8. Research, develop, and post a new webpage ([www.boulderfriendsmeeting.org/ipc-healingsteps](http://www.boulderfriendsmeeting.org/ipc-healingsteps)) offering resources to encourage Friends and others to consider appropriate actions or processes for acknowledgement, apology, atonement, truth and reconciliation, restorative justice, and community healing. Gather and post information about Native approaches to these processes. Consider designing a workshop where participants would create plans for carrying out such actions and processes.
9. Help organize activities to commemorate Indigenous Peoples Day in Boulder, annually on the second Monday of October, and take steps toward truth, reconciliation, and healing between the City and the Arapaho people, whose homeland is the Boulder Valley.
10. Engage with Quaker meetings, organizations, schools, and colleges about Indigenous peoples’ concerns generally, and specifically about the Doctrine of Discovery, the UN Declaration on the Rights of Indigenous Peoples, the impacts of the Indian Boarding Schools, as well as the roles Friends have played in these issues and ways that Friends can contribute to genuine healing processes.
11. Develop partnerships with other faith communities to carry the Toward Right Relationship with Native Peoples ministry into wider faith circles.
12. Develop partnerships with Native American organizations, schools, and colleges to offer the TRR workshops and to promote truth, reconciliation, and healing within Native communities.
13. Continue to develop and maintain three TRR websites ([www.boulderfriendsmeeting.org/ipc-right-relationship](http://www.boulderfriendsmeeting.org/ipc-right-relationship); [www.boulderfriendsmeeting.org/ipc-boarding-school-research](http://www.boulderfriendsmeeting.org/ipc-boarding-school-research); www.boulderfriendsmeeting.org/ipc-healingsteps) and enhance TRR’s presence on Facebook and perhaps other social media.
14. Undertake new project initiatives as guided by the IPC committee, Native American advisors, Quaker organizations, and the Inward Light.
15. Meet monthly with the IPC committee and the Spiritual Care Committee, and quarterly with the Oversight Committee. Submit quarterly program/financial reports and post them on the TRR website. Give verbal reports to Boulder Meeting at the invitation of the clerk.

**Proposed 2017 Budget**

**October 1, 2016 - Sept. 30, 2017 (Fourth Year)**

**Income sources:**

 Workshops (honorariums, expense reimbursement, participant donations) 10,000.

 Individuals 21,200.

 Boulder Friends Meeting, IPC, P&SJ 800.

 Grants 25.750.

 **Total project income** **$57,750.**

(Note: If any funds are given to the project director personally, she signs them over to the Toward Right Relationship Fund so that the Boulder Meeting can manage all project finances.)

**Project Expenses (for one-year project period)**

Contractor, Director of Toward Right Relationship project $50,000.

Consultants and Services 2,000.

 (TRR Outreach Coordinators, Video, Social Media, etc.)

Travel (5 plane trips plus ground transportation, $550x5) 2,750.

Conference fees (FGC, FAHE, Other) 1,500.

Office supplies and printing 1,500.

**Total expenses** **$57,750.**

**Budget Notes:**

**Contractor compensation:** Paula receives no benefits or insurance and pays all federal and state taxes. Compensation is less than 50% of an average salary package for this job description, amounting to a significant financial contribution from her to the project.

**Consultants and Services:** this line item offers very minimal compensation for Native American Outreach Coordinators Jerilyn DeCoteau and Doreen Martinez and Episcopal Outreach Coordinator Ann Cairns, who donate their very valuable professional services to the project. We may also contract consultants for technical and social media work.

**Personnel costs** are greatly reduced by the labor of volunteers. Larry Bangs voluntarily contributes data entry and communications. Trained and certified TRR workshop facilitators volunteer their time. IPC committee members and dozens of additional Friends facilitate and participate in workshop presentations. The meeting’s treasurer and bookkeeper and members of the Oversight committee contribute their skills in program and financial management. The Spiritual Care committee meets with the contractor monthly.

**Travel** includes airfare for 5 trips to present workshops (these costs will be reimbursed by the host organizations; see workshop income above.) Cost of travel is reduced by in-kind donations. Local workshop organizers arrange for some ground transportation, some meals, and all lodging. Gifts of frequent flyer miles and travel vouchers can also cut travel costs.

**Conference fees** are for conferences where Paula is presenting workshops or talks

**Total 2017 Budget** is 4% higher than the 2016 project budget. The project has met its budget for the past three years, building confidence in our ability to raise sufficient funds to carry the work forward.

**Project Director’s Projected Time Allocation 2014 2015 2016 2017**

**Administration** 5% 5% 5% 5%

 Compose written and verbal financial and program reports

 Keep workshop participation and evaluations records

 Meet with IPC, Oversight Committee, Spiritual Care Committee

**Fund Raising** 10% 30% 20% 10%

 Research and write grant proposals

 Solicit individual donations

 Develop and carry out crowdsourcing

 Develop and carry out social media

 Networking

**The Workshops**  75% 55% 30% 35%

 Create and circulate publicity and correspondence

 Rehearsals, presentations, and follow-up correspondence

 Travel

 Develop training process for volunteer facilitators

 Train, certify, coach new workshop facilitators

 New workshop development

**Quaker Indian School Research and Dissemination** 40% 25%

 Conduct field research at sites of Quaker Indian schools \*

 Conduct bibliographic research as Cadbury Scholar, Pendle Hill\*

 Write and submit articles for publication

 Develop and deliver powerpoint presentations and lectures

 Coordinate with National Native American Boarding School Healing Coalition

**Program Development**  10% 10% 5% 25%

 Meet with Native American and other program advisors

 Research appropriate apology, restorative justice, T&R processes

 Design webpage for models of apology, restorative justice, T&R processes

 Explore and develop partnerships

\*these activities were completed prior to FY2017